## Sheet1
Category | Control | Standard References | Likelihood | Impact | Score | Recommendation
On-Premise Lakehouse | Confirm classification of information assets (data sensitivity levels) | ISO 27001 A.5.12 | 3 | 3 | 9 | Implement formal data classification scheme for complexly mixed public election data
On-Premise Lakehouse | Assess PostgreSQL database access controls: Role-based access enforcement | NIST 800-53 AC-2 | 4 | 4 | 16 | Configure custom roles beyond docker-compose defaults, eliminate default credentials
On-Premise Lakehouse | Assess PostgreSQL database access controls: MFA enforcement status | NIST 800-53 AC-2 | 4 | 4 | 16 | Implement MFA beyond basic authentication via Docker environment variables
On-Premise Lakehouse | Examine network segmentation: Public vs private network boundaries | ISO 27001 A.8.22 | 4 | 3 | 12 | Implement network segmentation beyond localhost exposure (ports 8080, 9090, 9091)
On-Premise Lakehouse | Examine network segmentation: Firewall/endpoint protections | ISO 27001 A.8.20 | 4 | 3 | 12 | Configure firewall rules in docker-compose beyond host-level protection only
On-Premise Lakehouse | Review GPU and computing cluster security configurations | ISO 27001 A.8.9 | 3 | 3 | 9 | Apply security hardening to Spark cluster beyond default configurations
Public-Facing Site | Validate Google Analytics compliance with privacy standards: Presence/absence of consent banner | GDPR Art. 7 - 1 | 2 | 4 | 8 | Implement consent banner or cookie notice on static website
Public-Facing Site | Validate Google Analytics compliance with privacy standards: Privacy policy publicly available | GDPR Art. 12 - 1 | 2 | 4 | 8 | Add privacy policy link to website
GitHub Repo/CI/CD | Review CI/CD pipeline for secure deployment: Branch protection | ISO 27001 A.5.15 | 3 | 3 | 9 | Implement branch protection rules beyond single contributor direct push to main
GitHub Repo/CI/CD | Review CI/CD pipeline for secure deployment: Dependency and secrets scanning enabled | ISO 27001 A.8.9 | 3 | 3 | 9 | Configure GitHub Actions workflows for security scanning
GitHub Repo/CI/CD | Confirm repo access management: Role-based permissions | ISO 27001 A.5.15 | 2 | 2 | 4 | Establish formal access management policies beyond single owner repository
GitHub Repo/CI/CD | Validate branch protection and pull request policies | ISO 27001 A.8.9 | 3 | 3 | 9 | Implement pull request requirements and branch protection beyond direct commits to main
GitHub Repo/CI/CD | Check CI/CD pipeline security scans: Dependency scanning | ISO 27001 A.8.9 | 3 | 3 | 9 | Configure automated dependency vulnerability scanning
GitHub Repo/CI/CD | Check CI/CD pipeline security scans: Secrets scanning | ISO 27001 A.8.9 | 3 | 3 | 9 | Enable secrets scanning beyond .env file credential handling
Security Controls | MFA enforcement across critical systems | NIST 800-53 AC-2 | 4 | 4 | 16 | Implement MFA on Airflow, MinIO, PostgreSQL beyond default credentials
Security Controls | Review incident response process: Ad hoc incident management | ISO 27001 A.8.15 | 2 | 4 | 8 | Document formal incident response procedures
Security Controls | Review incident response process: Annual incident response plan review | ISO 27001 A.8.16 | 2 | 4 | 8 | Create incident response plan for annual review
GDPR Compliance | Assess privacy policy and cookie consent mechanisms: Presence of public privacy policy | GDPR Art. 12, 13, 14 | 2 | 4 | 8 | Implement public privacy policy on website
GDPR Compliance | Assess privacy policy and cookie consent mechanisms: Implementation of consent banner for analytics | GDPR Art. 7 | 2 | 4 | 8 | Implement consent banner on static website
Risk Management | Review Risk Register for identified High and Medium risks: MFA | ISO 27001 A.5.15 | 3 | 4 | 12 | Document MFA risk in formal risk register
Risk Management | Review Risk Register for identified High and Medium risks: Consent banner on site | ISO 27001 A.5.15 | 2 | 3 | 6 | Formally assess consent management risk on website
Risk Management | Confirm risk mitigation plans and timelines | ISO 27001 A.5.1 | 2 | 3 | 6 | Document formal risk management framework and mitigation plans
Risk Management | Verify monitoring and update cycles for risk register | ISO 27001 A.8.16 | 2 | 3 | 6 | Create risk register monitoring and update procedures